# Final Financial Audit

Project ID: P1048-Nishio MY PX33 TOTO

Finance & Project Controls

22 May 2025

Table of Contents

# 1	Executive Summary

This Final Financial Audit compares the original estimate in project_budget.md against realized costs in actual_costs.md for Project P1048-Nishio MY PX33 TOTO.

## 1.1	Key Result

- Budget (normalized with actual FX): RM89,777.50

- Actual: RM108,656.09

- Variance: +RM18,878.59 (+21.03%)

## 1.2	Primary Drivers of Overrun

- Installation Labor: +RM16,012.50 (+500.00%)

- Shipment: +RM3,243.00 (+300.28%)

- Travel: +RM1,448.00 (+72.40%)

## 1.3	Offsets (Underruns)

- Pre-Sales: -RM1,255.91 (-19.32%)

- Tax/Custom Duty: -RM644.00 (-19.88%)

## 1.4	Audit Opinion

Costs are arithmetically consistent with provided records and FX assumptions. The project exceeded budget primarily due to scope/time expansion in installation and logistics underestimation in the planning baseline.

# 2	Scope, Basis, and Methodology

## 2.1	Scope

This audit covers all cost categories explicitly listed in:

- project_budget.md (budget estimate)

- actual_costs.md (final actuals)

## 2.2	Currency and Normalization Basis

- Functional comparison currency: RM

- Applied FX for audit normalization: USD1 = RM4.27 (same as actual cost document, dated 22 May 2025)

## 2.3	Source Data Integrity Notes

- Budget document left labor totals as “TBD” pending FX.

- Actual document provided complete RM totals and category breakdown.

- For comparability, labor budget values were converted using RM4.27.

## 2.4	Normalized Budget Labor Conversion

- Development labor budget: USD4,500 × 4.27 = RM19,215.00

- Installation labor budget: USD750 × 4.27 = RM3,202.50

## 2.5	Financial Control Objective

Assess:

- Arithmetic correctness

- Budget realism vs actual execution

- Variance concentration and control lessons

# 3	Detailed Budget vs Actual Variance Analysis

## 3.1	Category-Level Comparison

| Category | Budget (RM) | Actual (RM) | Variance (RM) | Variance % |
| --- | --- | --- | --- | --- |
| Hardware & Material | 54,000.00 | 54,028.00 | +28.00 | +0.05% |
| Development Labor | 19,215.00 | 19,215.00 | 0.00 | 0.00% |
| Installation Labor | 3,202.50 | 19,215.00 | +16,012.50 | +500.00% |
| Pre-Sales | 6,500.00 | 5,244.09 | -1,255.91 | -19.32% |
| Travel | 2,000.00 | 3,448.00 | +1,448.00 | +72.40% |
| Shipment | 1,080.00 | 4,323.00 | +3,243.00 | +300.28% |
| Tax / Custom Duty | 3,240.00 | 2,596.00 | -644.00 | -19.88% |
| Miscellaneous | 540.00 | 587.00 | +47.00 | +8.70% |
| TOTAL | 89,777.50 | 108,656.09 | +18,878.59 | +21.03% |

## 3.2	Concentration of Total Overrun

- Installation Labor: 84.82% of net overrun

- Shipment: 17.18%

- Travel: 7.67%

- Offsets from underruns (Pre-Sales, Tax) reduced net overrun by 10.63%

## 3.3	Cost Structure Shift

- Labor intensity increased significantly due to installation duration expansion.

- Logistics costs (travel + shipment) materially exceeded planning assumptions.

- Hardware cost remained effectively on budget, indicating stable procurement execution.

# 4	Findings, Root Causes, and Control Assessment

## 4.1	Finding A — Installation Labor Underestimated

- Budget basis: 40 hours (5 workdays equivalent)

- Actual basis: 30 calendar days

- Result: +RM16,012.50 variance

Assessment: Baseline likely did not reflect realistic field installation duration and site conditions.

## 4.2	Finding B — Shipment Budget Formula Too Simplistic

- Budget basis: 2% of hardware cost = RM1,080

- Actual shipment: RM4,323

- Result: +RM3,243.00

Assessment: Percentage proxy did not capture freight, handling, insurance, and route/site factors.

## 4.3	Finding C — Travel Underestimation

- Budget: RM2,000 (4 trips × RM500)

- Actual: RM3,448

- Result: +RM1,448.00

Assessment: Trip count and/or per-trip costs were underestimated.

## 4.4	Finding D — Positive Controls

- Hardware variance: +0.05%

- Development variance: 0.00%

Assessment: Procurement and core development estimation were accurate.

## 4.5	Control Effectiveness Rating

- Strong: Development estimation, hardware procurement pricing

- Moderate: Tax projection, pre-sales planning

- Weak: Installation effort forecast, logistics modeling

## 4.6	Compliance and Arithmetic Validation

Recalculations confirm:

- Category totals match provided source values.

- FX conversion applications are consistent.

- Grand total RM108,656.09 is internally consistent.

# 5	Recommendations and Forward Controls

## 5.1	Budgeting Improvements

- Installation WBS model (mobilization, integration, testing, standby, rework allowance)

- Logistics costing model using vendor lane quotes and insurance

- Travel matrix by role, purpose, duration, regional rates

## 5.2	Governance Improvements

- Stage-gate reforecasting at award, pre-installation, and midpoint execution

- Variance triggers at 15% or RM1,000 (whichever is lower)

- Separated contingency pools (labor risk vs logistics volatility)

## 5.3	Baseline for Similar Future Projects

- Keep current development-rate method.

- Re-baseline installation using empirical duration from this project.

- Build logistics from actual invoices and route profiles.

## 5.4	Final Conclusion

Project delivery incurred a 21.03% total cost overrun relative to normalized budget. The overrun is primarily structural, driven by installation and logistics planning assumptions rather than uncontrolled procurement or development effort.

## 5.5	Sign-Off

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| [Name] | Finance Manager | __________ | __________ |
| [Name] | Project Manager | __________ | __________ |
| [Name] | Internal Auditor | __________ | __________ |

# 6	Appendix A — Calculation Detail

## 6.1	A1. Budget Total (Normalized to RM)

- Hardware: RM54,000.00

- Development: USD4,500 × 4.27 = RM19,215.00

- Installation: USD750 × 4.27 = RM3,202.50

- Pre-Sales: RM6,500.00

- Travel: RM2,000.00

- Shipment: RM1,080.00

- Tax: RM3,240.00

- Misc: RM540.00

Total Budget = RM89,777.50

## 6.2	A2. Actual Total

Per actual_costs.md:

- Development: RM19,215.00

- Installation: RM19,215.00

- Pre-Sales: RM5,244.09

- Hardware: RM54,028.00

- Travel: RM3,448.00

- Shipment: RM4,323.00

- Tax: RM2,596.00

- Misc: RM587.00

Total Actual = RM108,656.09

## 6.3	A3. Net Variance

RM108,656.09 − RM89,777.50 = RM18,878.59 (+21.03%)